## READ ME April 2024
Download the Reltio MVP plan to begin planning your implementation.
Update Customer Name and Owners as documented in your Service Order.
This Reltio MVP Plan is a template. Esnure you are updating your project plan with Customer specific details including but not limited to, entity types, additional match tuning iterations, project specific deployment activity steps, and links to Customer specific deliverables
The Sprint Plan template contains links to templates of the corresponding deliverables in Column B. As Customer specific deliverables are created, provide the appropriate link in Column B.
These tasks are to be leveraged whether the project is Reltio Professional Services led, Partner led, or Customer led. Adjust the owners of each task if and as needed.
Use this template as is, or upload to tool of choice (SmartSheets, MS Project, etc.)

## Reltio 90 Day MVP Project Plan
PHASE: Reltio 90 Day MVP
|  |  | Visualize |  | Model | Construct |  |  |  |  | Commission |  |  | Support
|  |  | Sprint 0 | Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4 |  | Sprint 5 |  | Sprint 6
Task | Deliverable | Owner | Week 0 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
|  |  | DD-Mnth | DD-Mnth | DD-Mnth | DD-Mnth | DD-Mnth | DD-Mnth | DD-Mnth | DD-Mnth | DD-Mnth | DD-Mnth | DD-Mnth | DD-Mnth | DD-Mnth
Sprint 0 - Customer Readiness
Complete Project Initiation Checklist | Reltio Project Initiation Checklist | Technical Delivery Manager
Confirm Customer Admin has received tenant/asset information and approves Implementation Team access to the tenants |  | Technical Delivery Manager
Review of data set to be loaded in Week1 |  | Technical Consultant
Review Readiness Checklist | Reach out to Practice Director for Customer's checklist started in sales process | Technical Delivery Manager
Review the MVP Risk Mitigation Document and update with any additional mitigations specific to the Customer | MVP Risk Mitigation Document | Technical Delivery Manager
Download and review MVP Plan and The Reltio Way Delivery Methodology with Customer |  | Technical Delivery Manager
Review Go Live Readiness Assessment with Customer and set expectation of how this is populated | Go Live Readiness Assessment | Technical Delivery Manager
Review Industry Standard Functional Requirements and Customer Non Functional Requirements with Customer | Standardized Requirements Document | Technical Delivery Manager
Document gap analysis of industry solution vs requirements | Fit / Gap Analysis Template | Solution Architect
Update MVP Plan as necessary (adding correct domains, entity types, etc.) |  | Technical Delivery Manager
Align on target date for Reltio Architecture Review Board and add to the Project Plan | Reltio Architecture Review Board | Technical Delivery Manager
Download and review MVP User Stories with Customer |  | Technical Delivery Manager
Update MVP User Stories as necessary (adding correct domains, entity types, etc.) |  | Technical Delivery Manager
Prepare for Project Kickoff | Reltio Engagement Kickoff Deck Template | Solution Architect
Hold Reltio Kickoff / PS Introduction Meeting | Reltio Engagement Kickoff Deck Template | Technical Delivery Manager
Data Quality Dashboard
Review dataset provided by Customer from Sprint 0 |  | Solution Architect
Load Source System data into Reltio via Console Data Loader or RIH |  | Technical Consultant
Validate data loaded correctly |  | Technical Consultant
Demo (and record) the Interactive Data Quality Dashboard to Customer business and technical resources |  | Technical Consultant
Document outcomes and Customer feedback of value milestone | Internal Transition _ Hand-off from PS template (Reltio PS uses this template) | Technical Delivery Manager
MILESTONE 1 - Data Awareness
Data Model
Review Industry Requirements document with implementation team | Standardized Requirements Document | Solution Architect
Document feedback on additional Customer specific requirements | Reltio Feedback Document Template | Solution Architect
Review gap analysis of industry solution vs requirements with implementation team | Fit / Gap Analysis Template | Solution Architect
Review data profiling results from Sprint 0 |  | Solution Architect
Review the solution attributes, entity types, and relationships | Solution documentation/technical specs | Solution Architect
Review API Latency template with customers, set expectations with customer about the process for performance estimates and what parameters impact performance. Ask customers about use cases and SLA that may affect latency. | API Latency Estimation Template | Solution Architect
Document required customer specific attributes | Reltio Solution Design Document Template | Solution Architect
Document customer specific Reference data (RDM) lookup types | Reltio Solution Design Document Template | Solution Architect
Hold Reltio Architecture Review Board (to align with finalization of match rule design) | Reltio Architecture Review Board | Solution Architect
Configuration of defined entities | Reltio Unit Test Script Template | Technical Consultant
Configuration of defined attributes | Reltio Unit Test Script Template | Technical Consultant
Configuration of relationships | Reltio Unit Test Script Template | Technical Consultant
Migrate Configuration to TEST | Reltio Unit Test Script Template | Technical Consultant
MVP Inbound Integration
Review Industry Requirements document and Fit / Gap Analysis from Sprint 0 with implementation team | Standardized Requirements Document | Solution Architect
Document feedback on additional Customer specific requirements | Reltio Feedback Document Template | Solution Architect
Review gap analysis of industry solution vs requirements with implementation team | Fit / Gap Analysis Template | Solution Architect
Document Data Flow Diagram between inbound Source Systems and Reltio | Reltio Solution Design Document Template | Solution Architect
Configure Integration Scheduler | Reltio Unit Test Script Template | Technical Consultant
Unit Test Inbound | Reltio Unit Test Script Template | Technical Consultant
Unit Test Outbound | Reltio Unit Test Script Template | Technical Consultant
Migrate Reltio Components to TEST | Reltio Unit Test Script Template | Technical Consultant
Load 1 Source System to TEST (Inbound) | Reltio Unit Test Script Template | Technical Consultant
Integrate Reltio UID to 1 Source System (Outbound) | Reltio Unit Test Script Template | Technical Consultant
Validate Reltio ID Successfully Loaded to Source | Reltio Unit Test Script Template | Technical Consultant
Gather information like API to be used, parameters (attributes, RDM, nested and reference attributes, entities, batch size, crosswalks/entity, RDM lookups/entity, match rules, simple attributes/entity, size of response for GET calls, number of filters, depth for tree endpoint) | API Latency Estimation Template | Solution Architect
Calculate latency estimate using the API latency template | API Latency Estimation Template | Solution Architect
Share estimate with customers | API Latency Estimation Template | Solution Architect
Reference Data Management (RDM)
Review Industry Requirements document and Fit / Gap Analysis from Sprint 0 with implementation team | Reltio Feedback Document Template | Solution Architect
Review gap analysis of industry solution vs requirements with implementation team | Fit / Gap Analysis Template | Solution Architect
Review Data Profiling for Sources |  | Solution Architect
Determine naming convention for lookup codes |  | Solution Architect
Identify source systems |  | Solution Architect
Review list of solution lookup codes with implementation team |  | Solution Architect
Confirm common or standardized values |  | Solution Architect
Document RDM Design in Reltio Solution Design Document | Reltio Solution Design Document Template | Solution Architect
Add source systems to RDM |  | Technical Consultant
Configure required Customer specific RDM lookup types |  | Technical Consultant
Load RDM lookup codes and canonical values |  | Technical Consultant
Update L3 data model to use lookup codes |  | Technical Consultant
Migrate Configuration to TEST | Reltio Unit Test Script Template | Technical Consultant
Address Standardization
Review Industry Requirements document and Fit / Gap Analysis from Sprint 0 with implementation team | Reltio Feedback Document Template | Solution Architect
Review gap analysis of industry solution vs requirements with implementation team | Fit / Gap Anlaysis Template | Solution Architect
Verify that the Reltio configuration (L1-L3) has mapping for Address Cleansing |  | Technical Consultant
Verify that Address Cleansing is working | Reltio Unit Test Script Template | Technical Consultant
Verify OOTB survivorship for Reltio cleanser wins |  | Technical Consultant
If project is requiring changes to address attributes, document the changes required | Reltio Solution Design Document Template | Solution Architect
If Loqate key allows for more than US addresses, verify each country code separately |  | Technical Consultant
Migrate Configuration to TEST | Reltio Unit Test Script Template | Technical Consultant
Match Rule Configuration & Tuning
Review Industry Requirements document and Fit / Gap Analysis from Sprint 0 with implementation team | Reltio Feedback Document Template | Solution Architect
Review gap analysis of industry solution vs requirements with implementation team | Fit / Gap Anlaysis Template | Solution Architect
Review data profiling results from Sprint 0 |  | Solution Architect
Document required Customer specific Match Rule Design in Reltio Solution Design Document | Reltio Solution Design Document Template | Solution Architect
Hold Match Rule Tuning Overview (if Needed) |  | Technical Delivery Manager
Communicate Customer Responsibilities |  | Technical Delivery Manager
Validate solution match rules | Ensure Match Rules are Configured Per Reltio Training Modules | Solution Architect
Configure required Customer specific Match Rules | Reltio Unit Test Script Template | Technical Consultant
Execute Clean Data Load to Prepare for Match Tuning |  | Technical Consultant
Clear Match Tables |  | Technical Consultant
Rebuild Match Tables |  | Technical Consultant
Execute & Analyze Match Rule Results Using Match Rule Analyzer |  | Technical Consultant
Generate Potential Match Report for Review by Data Stewards |  | Technical Consultant
Execute & Review Match Analysis Through UI Console |  | Technical Consultant
Match Tuning Iteration 1 With Customer: |  | Technical Consultant
Hold Overview to Review Potential Match Report |  | Technical Consultant
Document Feedback Provided By Customer |  | Technical Consultant
Update Match Rule Configuration Based on Internal Review |  | Technical Consultant
Clear Match Tables |  | Technical Consultant
Rebuild Match Tables |  | Technical Consultant
Execute & Analyze Match Rule Results Using Match Rule Analyzer |  | Technical Consultant
Generate Potential Match Report for Review by Data Stewards |  | Technical Consultant
Execute & Review Match Analysis Through UI Console |  | Technical Consultant
Match Tuning Iteration 2 With Customer: |  | Technical Consultant
Hold Overview to Review Potential Match Report |  | Technical Consultant
Document Feedback Provided By Customer |  | Technical Consultant
Update Match Rule Configuration Based on Internal Review |  | Technical Consultant
Clear Match Tables |  | Technical Consultant
Rebuild Match Tables |  | Technical Consultant
Execute & Analyze Match Rule Results Using Match Rule Analyzer |  | Technical Consultant
Generate Potential Match Report for Review by Data Stewards |  | Technical Consultant
Execute & Review Match Analysis Through UI Console |  | Technical Consultant
Migrate Configuration to TEST | Reltio Solution Design Document Template | Technical Consultant
Survivorship
Review Industry Requirements document and Fit / Gap Analysis from Sprint 0 with implementation team | Reltio Feedback Document Template | Solution Architect
Review gap analysis of industry solution vs requirements with implementation team | Fit / Gap Anlaysis Template | Solution Architect
Review security requirements related to changing survivorships | Reltio Feedback Document Template | Solution Architect
Document required Customer specific survivorship rule design in Reltio Solution Design Document | Reltio Solution Design Document Template | Solution Architect
Configure required Customer specific Survivorship Rules | Reltio Unit Test Script Template | Technical Consultant
Configure user roles (as needed for role-based survivorship) |  | Technical Consultant
Test the expected behavior of Customer specific survivorship rule configured | Reltio Unit Test Script Template | Technical Consultant
Review & collect feedback on results with customer |  | Technical Consultant
Update configuration based on end user feedback, if needed |  | Technical Consultant
Migrate Configuration to TEST | Reltio Unit Test Script Template | Technical Consultant
Completion of this module aligns with MILESTONE 2. Document outcomes and Customer feedback of value milestone | Internal Transition _ Hand-off from PS template (Reltio PS uses this template) | Technical Delivery Manager
UI Configuration
Review Industry Requirements document and Fit / Gap Analysis from Sprint 0 with implementation team | Reltio Feedback Document Template | Solution Architect
Review gap analysis of industry solution vs requirements with implementation team | Fit / Gap Anlaysis Template | Solution Architect
Hold OOTB Dashboard demo |  | Solution Architect
Create/edit baseline Profile views (by Entity type) | UI Configuration Guide | Technical Consultant
Configure Hierechy facets | UI Configuration Guide | Technical Consultant
Configure baseline Dashboard | UI Configuration Guide | Technical Consultant
Enable workflows |  | Technical Consultant
Demo UI to end users |  | Technical Consultant
Revise Profile views based on feedback |  | Technical Consultant
Revise Hierarchy views based on feedback |  | Technical Consultant
Revise Dashboard based on feedback |  | Technical Consultant
Revise Profile views based on feedback |  | Technical Consultant
Revise Hierarchy views based on feedback |  | Technical Consultant
Revise Dashboard based on feedback |  | Technical Consultant
Revise mobile UI based on feedback |  | Technical Consultant
Migrate Configuration to TEST | Reltio Unit Test Script Template | Technical Consultant
UI Enablement
Hold meeting to review enablement approach | Customer UI Enablement Approach Deck | Technical Delivery Manager
Identify resources to participate |  | Customer Manager
Schedule sessions |  | Technical Delivery Manager
Send instructions to register for Reltio Learn User Experience (if needed) |  | Technical Delivery Manager
Follow up that End Users have successfully registered via Reltio Learn |  | Technical Delivery Manager
Hold UI Enablement Sessions | Customer UI Enablement Approach Deck | Technical Delivery Manager
Send Summary Email after each session | 1 | Technical Delivery Manager
MILESTONE 2 - Reltio ID, Profile, and Relationships Generated
OOTB Workflow
Review Industry Requirements document and Fit / Gap Analysis from Sprint 0 with implementation team | Reltio Feedback Document Template | Solution Architect
Review gap analysis of industry solution vs requirements with implementation team | Fit / Gap Anlaysis Template | Solution Architect
Verify correct WorkflowPath is setup in environment | Postman or any other API calling tool | Technical Consultant
Verify that Tenant is registered with Workflow | Postman or any other API calling tool | Technical Consultant
Verify that ROLE_WORKFLOW, ROLE_REVIEWER, and ROLE_INITIATE_CHANGE_REQUEST are available for user assignment |  | Technical Consultant
Verify through the UI that a user with ROLE_WORKFLOW and ROLE_INITIATE_CHANGE_REQUEST can "SUGGEST" a change |  | Technical Consultant
Verify that a DCR has been created and assigned to any user with ROLE_REVIEWER role |  | Technical Consultant
Verify a user with ROLE_REVIEWER can approve the DCR | Reltio Unit Test Script Template | Technical Consultant
Document Workflow customization requirements if applicable | Workflow Customization Document | Technical Consultant
Migrate Configuration to TEST | Reltio Unit Test Script Template | Technical Consultant
Roles & Security
Verify that Customer Admin is identified and provisioned |  | Solution Architect
Finalized Roles & Security Matrix | Roles & Security Overview | Solution Architect
Define customer Groups, Roles and Permissions in Reltio User Management | Roles & Security Overview | Solution Architect
Define Advanced permissions (in Roles & Security Matrix) | Roles & Security Overview | Solution Architect
Update tenant permissions by using Reltio APIs |  | Technical Consultant
Document Roles & Security Design in Reltio Solution Design Document | Reltio Solution Design Document Template | Technical Consultant
Migrate Configuration to TEST | Reltio Unit Test Script Template | Technical Consultant
SSO
Hold meeting with Customer Security team to discuss steps to be considered in order to setup SSO on both Customer and Reltio side |  | Solution Architect
Customer SSO team needs “setup SSO with SAML (2.0) or OIDC for Reltio Application” in Identity Provider. IdP metadata.xml file will be shared by customer to Reltio team |  | Solution Architect
Login to Reltio Console and Launch SSO Configuration for SAML |  | Solution Architect
Enter following Configuration parameters appropriately: Default Settings: Email ID SAML attribute (SAML attribute that will be mapped to email id in Reltiomail) Roles (Roles assigned to all users in addition to user specific roles) Group (Groups assigned to all users in addition to user specific groups) Roles settings: Manage roles in IdP (Select when role assignments are managed in IdP) Groups settings: Manage groups in IdP (Select when group assignments are managed in IdP) IdP configuration: Upload Idp metadata.xml file (That was provided by Customer Idp team) |  | Solution Architect
Download and share METADATA.XML file to customer once SSO is Configured |  | Solution Architect
Customer SSO team to update the SSO setup in IdP with Reltio Entity ID and ACS URL available in Reltio METADATA.XML file |  | Customer SSO Team
Customer SSO team to share updated IdP metadata.xml file |  | Customer SSO Team
Login to Reltio Console and Launch SSO Configuration for SAML and upload updated metatadata.xml file |  | Solution Architect
Valid User launch Reltio and Login with Customer Credentials |  | Solution Architect
Reltio Admin assign appropriate Roles to user that was created in previous step |  | Solution Architect
User to Login into Reltio using SSO again |  | Solution Architect
Document SSO Design in Reltio Solution Design Document | Reltio Solution Design Document Template | Solution Architect
Migrate Configuration to TEST | Reltio Unit Test Script Template | Technical Consultant
Snowflake Connector for Downstream Integration
Review Industry Requirements document and Fit / Gap Analysis from Sprint 0 with implementation team | Standardized Requirements Document | Solution Architect
Review gap analysis of industry solution vs requirements with implementation team | Fit / Gap Analysis Template | Solution Architect
Integrate cloud storage | Configure the Reltio Snowflake Connector page of Reltio Documentation portal | Technical Consultant
Connect Snowflake to cloud storage | Configure the Reltio Snowflake Connector page of Reltio Documentation portal | Technical Consultant
Configure Snowflake with Reltio data from cloud storage | Configure the Reltio Snowflake Connector page of Reltio Documentation portal | Technical Consultant
Validate and sync Reltio data with Snowflake | Configure the Reltio Snowflake Connector page of Reltio Documentation portal | Technical Consultant
Migrate Configuration to TEST | Reltio Unit Test Script Template | Technical Consultant
Test Strategy & Execution
Hold first testing strategy meeting with Customer |  | Technical Delivery Manager
Confirm if existing testing strategy in place and if yes, review |  | Customer Manager
If no existing strategy in place, review Reltio template | Test Strategy Template | Customer Manager
Review Standardized Functional Test Scripts with Customer and Partner | Standardized Functional Test Scripts | Technical Delivery Manager
Review Customer definitions of SIT, UAT, Performance, etc Testing | Test Strategy Template | Customer Manager
Review RACI for SIT and UAT | Test Strategy Template | Technical Delivery Manager
Customer create SIT Test Plans |  | Customer Testing Team
Customer create UAT Test Plan |  | Customer Testing Team
Review SIT Test Plan |  | Technical Delivery Manager
Review UAT Test Plan |  | Technical Delivery Manager
Schedule Weekly UAT Meeting |  | Technical Delivery Manager
Customer Execute SIT Test Cases |  | Customer Testing Team
SIT Defect Resolution |  | Technical Consultant
Review SIT Results |  | Customer Testing Team
Receive SIT Sign Off |  | Technical Delivery Manager
Customer Execute UAT Test Cases |  | Customer Testing Team
UAT Defect Resolution |  | Technical Consultant
Review UAT Results |  | Customer Testing Team
Receive UAT Sign Off | 1 | Technical Delivery Manager
Deployment Planning & Execution
Catalog pieces to to be deployed | Deployment Guidelines | Technical Consultant
Review Go Live Readiness Assessment for completeness | Go Live Readiness Assessment | Technical Delivery Manager
Backup relevant configuration of each piece to git/google drive |  | Technical Consultant
Review Deployment Plan with Customer | (created with Customer) | Solution Archictect
Copy each configuration to Test enviroment |  | Solution Archictect
Execute Unit Tests again for regression |  | Technical Consultant
Review Deployment Plan with Customer | (created with Customer) | Solution Architect
Notify Reltio Customer Engineering team of upcoming Go Live activities via Support Ticket at least 1 week prior to start of Go Live activities | Go Live Notification Support Ticket_TEMPLATE | Solution Architect
Copy each configuration to Prod environment |  | Solution Architect
Execute Unit Tests again for regression |  | Technical Consultant
Receive formal end of project sign off from Customer | End of Project Sign Off Template | Technical Delivery Manager
Completion of this module aligns with MILESTONE 3. Document outcomes and Customer feedback of value milestone | Internal Transition _ Hand-off from PS template (Reltio PS uses this template) | Technical Delivery Manager
Schedule Reltio Professional Services transtion and handoff meeting (internal and Customer facing) |  | Technical Delivery Manager
Hold Reltio Professional Services transition and handoff meeting (internal and Customer facing) | Customer Facing Hand-off from Reltio PS Template | Technical Delivery Manager
MILESTONE 3 - Reltio ID and profile ready for consumption
Hypercare Support